## Home Dashboard
WayPoint Project Tracker - Home Dashboard
Project Name | WayPoint
Methodology | Kanban
Ticket Format | WPT-001
Total Tickets |  | Backlog |  | Ready |  | In Progress |  | Testing
160 |  | 150 |  | 0 |  | 5 |  | 0
Done |  | Total Story Points |  | Completed SP |  | Remaining SP |  | Completion %
5 |  | 722 |  | 18 |  | 704 |  | 2.493%
Select Team Member | TBD | [7 empty] | Status | Count
[9 empty] | Backlog | 150
Assigned Tickets | Open Tickets | Completed Tickets | Assigned SP | Completed SP | Remaining SP | Completion % | In Progress | Testing | Ready | 0
136 | 136 | 0 | 620 | 0 | 620 | 0% | 0 | 0 | In Progress | 5
[9 empty] | Testing | 0
[9 empty] | Done | 5
Selected Team Member Tickets
Ticket ID | Type | Module | Title | Status | SP
WPT-024 | Story | Authentication | Password and logout management | Backlog | 5
WPT-025 | Task | Authentication | Create change password screen | Backlog | 3
WPT-026 | Task | Authentication | Create logout function | Backlog | 2
WPT-027 | Epic | Employer Portal | Employer Dashboard and Profile | Backlog | 0
WPT-028 | Story | Employer Profile | Employer profile management | Backlog | 8
WPT-029 | Task | Employer Profile | Create employer profile page | Backlog | 5
WPT-030 | Task | Employer Profile | Create edit company profile function | Backlog | 5
WPT-031 | Task | Employer Profile | Create employer profile API | Backlog | 5
WPT-032 | Story | Employer Dashboard | Employer home dashboard | Backlog | 8
WPT-033 | Task | Employer Dashboard | Show total jobs posted | Backlog | 3
WPT-034 | Task | Employer Dashboard | Show new applications count | Backlog | 3
WPT-035 | Task | Employer Dashboard | Show in progress Employees count | Backlog | 3
WPT-036 | Task | Employer Dashboard | Show hired Employees count | Backlog | 3
WPT-037 | Task | Employer Dashboard | Show event summary cards | Backlog | 3
WPT-038 | Epic | Employer Job Management | Employer Job Dashboard and Job Postings | Backlog | 0
WPT-039 | Story | Employer Job Management | View all job postings | Backlog | 8
WPT-040 | Task | Employer Job Management | Create job postings list page | Backlog | 5
WPT-041 | Task | Employer Job Management | Display job ID and job name | Backlog | 3
WPT-042 | Task | Employer Job Management | Display Employees applied count | Backlog | 3
WPT-043 | Task | Employer Job Management | Create clickable job ID navigation | Backlog | 3
WPT-044 | Story | Employer Job Management | Create new job posting | Backlog | 8
WPT-045 | Task | Employer Job Management | Create job posting form UI | Backlog | 5
WPT-046 | Task | Employer Job Management | Create save job posting API | Backlog | 5
WPT-047 | Task | Employer Job Management | Validate job posting fields | Backlog | 3
WPT-048 | Story | Employer Job Management | Edit existing job posting | Backlog | 5
WPT-049 | Task | Employer Job Management | Create edit job UI | Backlog | 3
WPT-050 | Task | Employer Job Management | Create update job API | Backlog | 5
WPT-051 | Story | Employer Job Management | Delete job posting | Backlog | 5
WPT-052 | Task | Employer Job Management | Create delete confirmation UI | Backlog | 2
WPT-053 | Task | Employer Job Management | Create delete job API | Backlog | 3
WPT-054 | Story | Employer Job Management | View Employees for a job | Backlog | 8
WPT-055 | Task | Employer Job Management | Create Employee applications list | Backlog | 5
WPT-056 | Task | Employer Job Management | Display application status | Backlog | 3
WPT-057 | Task | Employer Job Management | Create Employee details view | Backlog | 5
WPT-058 | Epic | Employer Application Tracking | Employer Employee Status Management | Backlog | 0
WPT-059 | Story | Employer Application Tracking | Update Employee application status | Backlog | 8
WPT-060 | Task | Employer Application Tracking | Create status dropdown for application | Backlog | 3
WPT-061 | Task | Employer Application Tracking | Create update application status API | Backlog | 5
WPT-062 | Task | Employer Application Tracking | Show status history or latest status | Backlog | 3
WPT-063 | Epic | Employer Event Management | Employer Event Dashboard and Events | Backlog | 0
WPT-064 | Story | Employer Event Management | View employer event dashboard | Backlog | 8
WPT-065 | Task | Employer Event Management | Show total events created | Backlog | 3
WPT-066 | Task | Employer Event Management | Show upcoming events count | Backlog | 3
WPT-067 | Task | Employer Event Management | Show completed events count | Backlog | 3
WPT-068 | Story | Employer Event Management | Create new event | Backlog | 8
WPT-069 | Task | Employer Event Management | Create event form UI | Backlog | 5
WPT-070 | Task | Employer Event Management | Create save event API | Backlog | 5
WPT-071 | Task | Employer Event Management | Validate event fields | Backlog | 3
WPT-072 | Story | Employer Event Management | View event details | Backlog | 8
WPT-073 | Task | Employer Event Management | Display event information | Backlog | 3
Note on A23: Looks up tickets for the selected team member using INDEX/AGGREGATE — works in all Excel versions, no dynamic arrays required.

## Tickets
Ticket ID | Parent ID | Type | Module | Title | Assignee | Status | Story Points | Created Date | Start Date | Target Date | Completed Date | Notes
WPT-001 |  | Epic | Project Foundation | WayPoint Application Foundation | Pragna | Done | 0 |  |  |  |  | Core application setup
WPT-002 | WPT-001 | Story | Project Foundation | Set up React full stack project structure | Pragna | Done | 5 |  |  |  |  | Create frontend and backend base structure
WPT-003 | WPT-002 | Task | Project Foundation | Create frontend React application | Pragna | Done | 3 |  |  |  |  | Set up app shell and routing
WPT-004 | WPT-002 | Task | Project Foundation | Create backend API project | Pragna | Done | 5 |  |  |  |  | Set up backend services
WPT-005 | WPT-002 | Task | Project Foundation | Set up database connection | Pragna | Done | 5 |  |  |  |  | Connect backend to database
WPT-006 | WPT-002 | Subtask | Project Foundation | Create environment configuration | Pragna | In Progress | 2 |  |  |  |  | Add dev/test/prod config placeholders
WPT-007 | WPT-001 | Story | Project Foundation | Create shared navigation layout | Pragna | In Progress | 5 |  |  |  |  | Common navbar for employer and Employee
WPT-008 | WPT-007 | Task | Shared UI | Create top navigation bar | Pragna | In Progress | 3 |  |  |  |  | Navbar with dashboard links
WPT-009 | WPT-007 | Task | Shared UI | Create profile icon menu | Pragna | In Progress | 3 |  |  |  |  | Profile
WPT-010 | WPT-007 | Task | Shared UI | Create reusable dashboard card component | Pragna | In Progress | 3 |  |  |  |  | Used for counts and summary metrics
WPT-011 |  | Epic | Authentication | Registration and Login | Pragna | Backlog | 0 |  |  |  |  | Employer and Employee authentication
WPT-012 | WPT-011 | Story | Authentication | Employer registration | Pragna | Backlog | 8 |  |  |  |  | Employer can create account
WPT-013 | WPT-012 | Task | Authentication | Create employer registration UI | Pragna | Backlog | 5 |  |  |  |  | Registration form
WPT-014 | WPT-012 | Task | Authentication | Create employer registration API | Pragna | Backlog | 5 |  |  |  |  | Save employer account
WPT-015 | WPT-012 | Task | Authentication | Validate employer registration fields | Pragna | Backlog | 3 |  |  |  |  | Required fields and email validation
WPT-016 | WPT-011 | Story | Authentication | Employee registration | Jhansi | Backlog | 8 |  |  |  |  | Employee can create account
WPT-017 | WPT-016 | Task | Authentication | Create Employee registration UI | Jhansi | Backlog | 5 |  |  |  |  | Registration form
WPT-018 | WPT-016 | Task | Authentication | Create Employee registration API | Jhansi | Backlog | 5 |  |  |  |  | Save Employee account
WPT-019 | WPT-016 | Task | Authentication | Validate Employee registration fields | Jhansi | Backlog | 3 |  |  |  |  | Required fields and email validation
WPT-020 | WPT-011 | Story | Authentication | Login for employer and Employee | Pragna | Backlog | 8 |  |  |  |  | Role based login
WPT-021 | WPT-020 | Task | Authentication | Create login UI | Pragna | Backlog | 3 |  |  |  |  | Common login screen
WPT-022 | WPT-020 | Task | Authentication | Create login API | Pragna | Backlog | 5 |  |  |  |  | Authenticate user
WPT-023 | WPT-020 | Task | Authentication | Redirect user based on account type | Jhansi | Backlog | 5 |  |  |  |  | Employer to employer dashboard Employee to Employee dashboard
WPT-024 | WPT-011 | Story | Authentication | Password and logout management | TBD | Backlog | 5 |  |  |  |  | Profile menu actions
WPT-025 | WPT-024 | Task | Authentication | Create change password screen | TBD | Backlog | 3 |  |  |  |  | Allow password change
WPT-026 | WPT-024 | Task | Authentication | Create logout function | TBD | Backlog | 2 |  |  |  |  | End user session
WPT-027 |  | Epic | Employer Portal | Employer Dashboard and Profile | TBD | Backlog | 0 |  |  |  |  | Employer side main experience
WPT-028 | WPT-027 | Story | Employer Profile | Employer profile management | TBD | Backlog | 8 |  |  |  |  | Employer can edit company information
WPT-029 | WPT-028 | Task | Employer Profile | Create employer profile page | TBD | Backlog | 5 |  |  |  |  | Company profile details
WPT-030 | WPT-028 | Task | Employer Profile | Create edit company profile function | TBD | Backlog | 5 |  |  |  |  | Update company name and details
WPT-031 | WPT-028 | Task | Employer Profile | Create employer profile API | TBD | Backlog | 5 |  |  |  |  | Save and fetch employer profile
WPT-032 | WPT-027 | Story | Employer Dashboard | Employer home dashboard | TBD | Backlog | 8 |  |  |  |  | Summary dashboard after login
WPT-033 | WPT-032 | Task | Employer Dashboard | Show total jobs posted | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-034 | WPT-032 | Task | Employer Dashboard | Show new applications count | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-035 | WPT-032 | Task | Employer Dashboard | Show in progress Employees count | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-036 | WPT-032 | Task | Employer Dashboard | Show hired Employees count | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-037 | WPT-032 | Task | Employer Dashboard | Show event summary cards | TBD | Backlog | 3 |  |  |  |  | Upcoming and completed events
WPT-038 |  | Epic | Employer Job Management | Employer Job Dashboard and Job Postings | TBD | Backlog | 0 |  |  |  |  | Employer can manage jobs
WPT-039 | WPT-038 | Story | Employer Job Management | View all job postings | TBD | Backlog | 8 |  |  |  |  | Employer can see job list
WPT-040 | WPT-039 | Task | Employer Job Management | Create job postings list page | TBD | Backlog | 5 |  |  |  |  | List view of jobs
WPT-041 | WPT-039 | Task | Employer Job Management | Display job ID and job name | TBD | Backlog | 3 |  |  |  |  | Columns in job list
WPT-042 | WPT-039 | Task | Employer Job Management | Display Employees applied count | TBD | Backlog | 3 |  |  |  |  | Show count per job
WPT-043 | WPT-039 | Task | Employer Job Management | Create clickable job ID navigation | TBD | Backlog | 3 |  |  |  |  | Open job details
WPT-044 | WPT-038 | Story | Employer Job Management | Create new job posting | TBD | Backlog | 8 |  |  |  |  | Employer can create job
WPT-045 | WPT-044 | Task | Employer Job Management | Create job posting form UI | TBD | Backlog | 5 |  |  |  |  | Job title description location etc.
WPT-046 | WPT-044 | Task | Employer Job Management | Create save job posting API | TBD | Backlog | 5 |  |  |  |  | Backend save logic
WPT-047 | WPT-044 | Task | Employer Job Management | Validate job posting fields | TBD | Backlog | 3 |  |  |  |  | Required fields
WPT-048 | WPT-038 | Story | Employer Job Management | Edit existing job posting | TBD | Backlog | 5 |  |  |  |  | Employer can update job
WPT-049 | WPT-048 | Task | Employer Job Management | Create edit job UI | TBD | Backlog | 3 |  |  |  |  | Modify existing job
WPT-050 | WPT-048 | Task | Employer Job Management | Create update job API | TBD | Backlog | 5 |  |  |  |  | Backend update logic
WPT-051 | WPT-038 | Story | Employer Job Management | Delete job posting | TBD | Backlog | 5 |  |  |  |  | Employer can delete job
WPT-052 | WPT-051 | Task | Employer Job Management | Create delete confirmation UI | TBD | Backlog | 2 |  |  |  |  | Prevent accidental deletion
WPT-053 | WPT-051 | Task | Employer Job Management | Create delete job API | TBD | Backlog | 3 |  |  |  |  | Backend delete logic
WPT-054 | WPT-038 | Story | Employer Job Management | View Employees for a job | TBD | Backlog | 8 |  |  |  |  | Employer can see applicants
WPT-055 | WPT-054 | Task | Employer Job Management | Create Employee applications list | TBD | Backlog | 5 |  |  |  |  | List applicants for selected job
WPT-056 | WPT-054 | Task | Employer Job Management | Display application status | TBD | Backlog | 3 |  |  |  |  | New In Review Shortlisted Hired Rejected
WPT-057 | WPT-054 | Task | Employer Job Management | Create Employee details view | TBD | Backlog | 5 |  |  |  |  | Open Employee profile/application
WPT-058 |  | Epic | Employer Application Tracking | Employer Employee Status Management | TBD | Backlog | 0 |  |  |  |  | Employer manages Employee status
WPT-059 | WPT-058 | Story | Employer Application Tracking | Update Employee application status | TBD | Backlog | 8 |  |  |  |  | Move Employees through hiring status
WPT-060 | WPT-059 | Task | Employer Application Tracking | Create status dropdown for application | TBD | Backlog | 3 |  |  |  |  | New In Review Shortlisted Hired Rejected
WPT-061 | WPT-059 | Task | Employer Application Tracking | Create update application status API | TBD | Backlog | 5 |  |  |  |  | Save status change
WPT-062 | WPT-059 | Task | Employer Application Tracking | Show status history or latest status | TBD | Backlog | 3 |  |  |  |  | Track current state
WPT-063 |  | Epic | Employer Event Management | Employer Event Dashboard and Events | TBD | Backlog | 0 |  |  |  |  | Employer manages career events
WPT-064 | WPT-063 | Story | Employer Event Management | View employer event dashboard | TBD | Backlog | 8 |  |  |  |  | Summary of events
WPT-065 | WPT-064 | Task | Employer Event Management | Show total events created | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-066 | WPT-064 | Task | Employer Event Management | Show upcoming events count | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-067 | WPT-064 | Task | Employer Event Management | Show completed events count | TBD | Backlog | 3 |  |  |  |  | Dashboard card
WPT-068 | WPT-063 | Story | Employer Event Management | Create new event | TBD | Backlog | 8 |  |  |  |  | Career fair or event posting
WPT-069 | WPT-068 | Task | Employer Event Management | Create event form UI | TBD | Backlog | 5 |  |  |  |  | Event name date location details
WPT-070 | WPT-068 | Task | Employer Event Management | Create save event API | TBD | Backlog | 5 |  |  |  |  | Backend save logic
WPT-071 | WPT-068 | Task | Employer Event Management | Validate event fields | TBD | Backlog | 3 |  |  |  |  | Required fields
WPT-072 | WPT-063 | Story | Employer Event Management | View event details | TBD | Backlog | 8 |  |  |  |  | Employer can open event ID
WPT-073 | WPT-072 | Task | Employer Event Management | Display event information | TBD | Backlog | 3 |  |  |  |  | Event detail screen
WPT-074 | WPT-072 | Task | Employer Event Management | Display registered Employees count | TBD | Backlog | 3 |  |  |  |  | Count of registrations
WPT-075 | WPT-072 | Task | Employer Event Management | Display registered Employee list | TBD | Backlog | 5 |  |  |  |  | Employee registration details
WPT-076 | WPT-063 | Story | Employer Event Management | Edit cancel postpone or delete event | TBD | Backlog | 8 |  |  |  |  | Employer can manage event lifecycle
WPT-077 | WPT-076 | Task | Employer Event Management | Create edit event function | TBD | Backlog | 3 |  |  |  |  | Update event details
WPT-078 | WPT-076 | Task | Employer Event Management | Create cancel event function | TBD | Backlog | 3 |  |  |  |  | Cancel event
WPT-079 | WPT-076 | Task | Employer Event Management | Create postpone event function | TBD | Backlog | 3 |  |  |  |  | Change event date
WPT-080 | WPT-076 | Task | Employer Event Management | Create delete event function | TBD | Backlog | 3 |  |  |  |  | Remove event
WPT-081 |  | Epic | Employee Portal | Employee Dashboard and Profile | TBD | Backlog | 0 |  |  |  |  | Employee side main experience
WPT-082 | WPT-081 | Story | Employee Profile | Employee profile management | TBD | Backlog | 8 |  |  |  |  | Employee can manage profile
WPT-083 | WPT-082 | Task | Employee Profile | Create Employee profile page | TBD | Backlog | 5 |  |  |  |  | Profile details
WPT-084 | WPT-082 | Task | Employee Profile | Create edit Employee profile function | TBD | Backlog | 5 |  |  |  |  | Update Employee details
WPT-085 | WPT-082 | Task | Employee Profile | Create resume upload function | TBD | Backlog | 8 |  |  |  |  | Upload resume
WPT-086 | WPT-082 | Task | Employee Profile | Create Employee profile API | TBD | Backlog | 5 |  |  |  |  | Save and fetch profile
WPT-087 | WPT-081 | Story | Employee Dashboard | Employee home dashboard | TBD | Backlog | 8 |  |  |  |  | Summary after login
WPT-088 | WPT-087 | Task | Employee Dashboard | Show my applications summary | TBD | Backlog | 3 |  |  |  |  | Application count and status
WPT-089 | WPT-087 | Task | Employee Dashboard | Show event registration summary | TBD | Backlog | 3 |  |  |  |  | Upcoming and completed events
WPT-090 | WPT-087 | Task | Employee Dashboard | Show notifications summary | TBD | Backlog | 3 |  |  |  |  | Recent alerts
WPT-091 |  | Epic | Employee Job Management | Employee Job Dashboard and Applications | TBD | Backlog | 0 |  |  |  |  | Employee applies for jobs
WPT-092 | WPT-091 | Story | Employee Job Management | Browse new job postings | TBD | Backlog | 8 |  |  |  |  | Employee can view available jobs
WPT-093 | WPT-092 | Task | Employee Job Management | Create job listings page | TBD | Backlog | 5 |  |  |  |  | List available jobs
WPT-094 | WPT-092 | Task | Employee Job Management | Create job search box | TBD | Backlog | 3 |  |  |  |  | Search by keyword
WPT-095 | WPT-092 | Task | Employee Job Management | Create job filters | TBD | Backlog | 5 |  |  |  |  | Filter by relevance newest etc.
WPT-096 | WPT-092 | Task | Employee Job Management | Create job description page | TBD | Backlog | 5 |  |  |  |  | Open job details
WPT-097 | WPT-091 | Story | Employee Job Management | Apply for a job | TBD | Backlog | 13 |  |  |  |  | Employee can submit application
WPT-098 | WPT-097 | Task | Employee Job Management | Create apply button and flow | TBD | Backlog | 3 |  |  |  |  | Start application process
WPT-099 | WPT-097 | Task | Employee Job Management | Allow apply using existing profile | TBD | Backlog | 5 |  |  |  |  | Use saved profile
WPT-100 | WPT-097 | Task | Employee Job Management | Allow apply by filling application form | TBD | Backlog | 5 |  |  |  |  | Manual application
WPT-101 | WPT-097 | Task | Employee Job Management | Allow resume upload during application | TBD | Backlog | 5 |  |  |  |  | Attach resume
WPT-102 | WPT-097 | Task | Employee Job Management | Create submit application API | TBD | Backlog | 8 |  |  |  |  | Save application
WPT-103 | WPT-091 | Story | Employee Job Management | Track my applications | TBD | Backlog | 8 |  |  |  |  | Employee sees submitted applications
WPT-104 | WPT-103 | Task | Employee Job Management | Create my applications tab | TBD | Backlog | 5 |  |  |  |  | Submitted applications list
WPT-105 | WPT-103 | Task | Employee Job Management | Display application status | TBD | Backlog | 3 |  |  |  |  | Submitted In Review Shortlisted Hired Rejected
WPT-106 | WPT-103 | Task | Employee Job Management | Create view application details screen | TBD | Backlog | 5 |  |  |  |  | Read-only application view
WPT-107 | WPT-103 | Task | Employee Job Management | Create withdraw application function | Giridhar | Backlog | 5 |  |  |  |  | Employee can withdraw
WPT-108 | WPT-103 | Task | Employee Job Management | Prevent editing after submission | TBD | Backlog | 3 |  |  |  |  | Read-only after apply
WPT-109 |  | Epic | Employee Event Management | Employee Event Dashboard and RSVP | TBD | Backlog | 0 |  |  |  |  | Employee registers for events
WPT-110 | WPT-109 | Story | Employee Event Management | Browse available events | TBD | Backlog | 8 |  |  |  |  | Employee can find events
WPT-111 | WPT-110 | Task | Employee Event Management | Create event listings page | TBD | Backlog | 5 |  |  |  |  | List events
WPT-112 | WPT-110 | Task | Employee Event Management | Create event search box | TBD | Backlog | 3 |  |  |  |  | Search by keyword
WPT-113 | WPT-110 | Task | Employee Event Management | Create event detail page | TBD | Backlog | 5 |  |  |  |  | Open event details
WPT-114 | WPT-109 | Story | Employee Event Management | Register for event | TBD | Backlog | 8 |  |  |  |  | Employee can RSVP
WPT-115 | WPT-114 | Task | Employee Event Management | Create RSVP/register button | TBD | Backlog | 3 |  |  |  |  | Register for event
WPT-116 | WPT-114 | Task | Employee Event Management | Create event registration API | TBD | Backlog | 5 |  |  |  |  | Save RSVP
WPT-117 | WPT-114 | Task | Employee Event Management | Show registered status | TBD | Backlog | 3 |  |  |  |  | Employee sees RSVP status
WPT-118 | WPT-109 | Story | Employee Event Management | Manage registered events | TBD | Backlog | 8 |  |  |  |  | Employee tracks event RSVPs
WPT-119 | WPT-118 | Task | Employee Event Management | Create registered events tab | TBD | Backlog | 5 |  |  |  |  | Events Employee registered for
WPT-120 | WPT-118 | Task | Employee Event Management | Show upcoming events | TBD | Backlog | 3 |  |  |  |  | Upcoming registrations
WPT-121 | WPT-118 | Task | Employee Event Management | Show completed events | TBD | Backlog | 3 |  |  |  |  | Past events
WPT-122 | WPT-118 | Task | Employee Event Management | Create cancel RSVP function | TBD | Backlog | 5 |  |  |  |  | Cancel registration
WPT-123 | WPT-118 | Task | Employee Event Management | Create add to calendar action | TBD | Backlog | 5 |  |  |  |  | Calendar action placeholder
WPT-124 |  | Epic | Notifications | Notifications for Employee and Employer | TBD | Backlog | 0 |  |  |  |  | Shared notification feature
WPT-125 | WPT-124 | Story | Notifications | Create notification center | TBD | Backlog | 8 |  |  |  |  | Users can view notifications
WPT-126 | WPT-125 | Task | Notifications | Create notifications UI | TBD | Backlog | 5 |  |  |  |  | List notifications
WPT-127 | WPT-125 | Task | Notifications | Create notification API | TBD | Backlog | 5 |  |  |  |  | Fetch user notifications
WPT-128 | WPT-125 | Task | Notifications | Show unread notification count | TBD | Backlog | 3 |  |  |  |  | Navbar or dashboard count
WPT-129 |  | Epic | Contact Support | Contact WayPoint Support | TBD | Backlog | 0 |  |  |  |  | Shared contact form
WPT-130 | WPT-129 | Story | Contact Support | Create Contact Us page | TBD | Backlog | 8 |  |  |  |  | Same feature for employer and Employee
WPT-131 | WPT-130 | Task | Contact Support | Create contact form UI | TBD | Backlog | 5 |  |  |  |  | Name email message category
WPT-132 | WPT-130 | Task | Contact Support | Create submit support ticket API | TBD | Backlog | 5 |  |  |  |  | Save support request
WPT-133 | WPT-130 | Task | Contact Support | Create confirmation message after submission | TBD | Backlog | 2 |  |  |  |  | Success message
WPT-134 | WPT-130 | Task | Contact Support | Create support ticket ID generation | TBD | Backlog | 3 |  |  |  |  | Generate support reference number
WPT-135 |  | Epic | Data Model and API | Database Tables and Core APIs | TBD | Backlog | 0 |  |  |  |  | Backend data foundation
WPT-136 | WPT-135 | Story | Data Model | Create user and role data model | TBD | Backlog | 8 |  |  |  |  | Employer and Employee users
WPT-137 | WPT-136 | Task | Data Model | Create users table | TBD | Backlog | 5 |  |  |  |  | Common user table
WPT-138 | WPT-136 | Task | Data Model | Create employer profile table | TBD | Backlog | 5 |  |  |  |  | Company details
WPT-139 | WPT-136 | Task | Data Model | Create Employee profile table | TBD | Backlog | 5 |  |  |  |  | Employee details and resume
WPT-140 | WPT-135 | Story | Data Model | Create jobs and applications data model | TBD | Backlog | 13 |  |  |  |  | Jobs and Employee applications
WPT-141 | WPT-140 | Task | Data Model | Create jobs table | TBD | Backlog | 5 |  |  |  |  | Job postings
WPT-142 | WPT-140 | Task | Data Model | Create applications table | TBD | Backlog | 5 |  |  |  |  | Employee applications
WPT-143 | WPT-140 | Task | Data Model | Create application status field | TBD | Backlog | 3 |  |  |  |  | Submitted In Review Shortlisted Hired Rejected
WPT-144 | WPT-135 | Story | Data Model | Create events and registrations data model | TBD | Backlog | 13 |  |  |  |  | Events and RSVPs
WPT-145 | WPT-144 | Task | Data Model | Create events table | TBD | Backlog | 5 |  |  |  |  | Employer events
WPT-146 | WPT-144 | Task | Data Model | Create event registrations table | TBD | Backlog | 5 |  |  |  |  | Employee event registrations
WPT-147 | WPT-144 | Task | Data Model | Create event status field | TBD | Backlog | 3 |  |  |  |  | Upcoming Completed Cancelled Postponed
WPT-148 |  | Epic | Quality Assurance | Testing and Validation | TBD | Backlog | 0 |  |  |  |  | QA coverage for application
WPT-149 | WPT-148 | Story | QA | Test employer portal flows | TBD | Backlog | 8 |  |  |  |  | Employer side testing
WPT-150 | WPT-149 | Task | QA | Test employer registration and login | TBD | Backlog | 3 |  |  |  |  | QA test
WPT-151 | WPT-149 | Task | QA | Test employer job management | TBD | Backlog | 5 |  |  |  |  | QA test
WPT-152 | WPT-149 | Task | QA | Test employer event management | TBD | Backlog | 5 |  |  |  |  | QA test
WPT-153 | WPT-148 | Story | QA | Test Employee portal flows | TBD | Backlog | 8 |  |  |  |  | Employee side testing
WPT-154 | WPT-153 | Task | QA | Test Employee registration and login | TBD | Backlog | 3 |  |  |  |  | QA test
WPT-155 | WPT-153 | Task | QA | Test job search and application flow | TBD | Backlog | 5 |  |  |  |  | QA test
WPT-156 | WPT-153 | Task | QA | Test event registration and cancellation | TBD | Backlog | 5 |  |  |  |  | QA test
WPT-157 | WPT-148 | Story | QA | Test shared features | TBD | Backlog | 5 |  |  |  |  | Shared testing
WPT-158 | WPT-157 | Task | QA | Test profile menu actions | TBD | Backlog | 3 |  |  |  |  | QA test
WPT-159 | WPT-157 | Task | QA | Test contact support form | TBD | Backlog | 3 |  |  |  |  | QA test
WPT-160 | WPT-157 | Task | QA | Test notifications | TBD | Backlog | 3 |  |  |  |  | QA test

## Team Members
Name | Role | Primary Skill | Active | Notes
Pragna | TBD | TBD | Yes | Update role/skill later
Vasavi | TBD | TBD | Yes | Update role/skill later
Niharika | TBD | TBD | Yes | Update role/skill later
Arun | TBD | TBD | Yes | Update role/skill later
Giridhar | TBD | TBD | Yes | Update role/skill later
Mahesh | TBD | TBD | Yes | Update role/skill later
Jhansi | TBD | TBD | Yes | Update role/skill later
Geethanjali | TBD | TBD | Yes | Update role/skill later
Mani | TBD | TBD | Yes | Update role/skill later
TBD | Unassigned | TBD | No | Default unassigned placeholder

## Kanban Board
WayPoint Kanban Board
Backlog | Ready | In Progress | Testing | Done
WPT-011 - Registration and Login |  | WPT-006 - Create environment configuration |  | WPT-001 - WayPoint Application Foundation
WPT-012 - Employer registration |  | WPT-007 - Create shared navigation layout |  | WPT-002 - Set up React full stack project structure
WPT-013 - Create employer registration UI |  | WPT-008 - Create top navigation bar |  | WPT-003 - Create frontend React application
WPT-014 - Create employer registration API |  | WPT-009 - Create profile icon menu |  | WPT-004 - Create backend API project
WPT-015 - Validate employer registration fields |  | WPT-010 - Create reusable dashboard card component |  | WPT-005 - Set up database connection
WPT-016 - Employee registration
WPT-017 - Create Employee registration UI
WPT-018 - Create Employee registration API
WPT-019 - Validate Employee registration fields
WPT-020 - Login for employer and Employee
WPT-021 - Create login UI
WPT-022 - Create login API
WPT-023 - Redirect user based on account type
WPT-024 - Password and logout management
WPT-025 - Create change password screen
WPT-026 - Create logout function
WPT-027 - Employer Dashboard and Profile
WPT-028 - Employer profile management
WPT-029 - Create employer profile page
WPT-030 - Create edit company profile function
WPT-031 - Create employer profile API
WPT-032 - Employer home dashboard
WPT-033 - Show total jobs posted
WPT-034 - Show new applications count
WPT-035 - Show in progress Employees count
WPT-036 - Show hired Employees count
WPT-037 - Show event summary cards
WPT-038 - Employer Job Dashboard and Job Postings
WPT-039 - View all job postings
WPT-040 - Create job postings list page
WPT-041 - Display job ID and job name
WPT-042 - Display Employees applied count
WPT-043 - Create clickable job ID navigation
WPT-044 - Create new job posting
WPT-045 - Create job posting form UI
WPT-046 - Create save job posting API
WPT-047 - Validate job posting fields
WPT-048 - Edit existing job posting
WPT-049 - Create edit job UI
WPT-050 - Create update job API
WPT-051 - Delete job posting
WPT-052 - Create delete confirmation UI
WPT-053 - Create delete job API
WPT-054 - View Employees for a job
WPT-055 - Create Employee applications list
WPT-056 - Display application status
WPT-057 - Create Employee details view
WPT-058 - Employer Employee Status Management
WPT-059 - Update Employee application status
WPT-060 - Create status dropdown for application
WPT-061 - Create update application status API
WPT-062 - Show status history or latest status
WPT-063 - Employer Event Dashboard and Events
WPT-064 - View employer event dashboard
WPT-065 - Show total events created
WPT-066 - Show upcoming events count
WPT-067 - Show completed events count
WPT-068 - Create new event
WPT-069 - Create event form UI
WPT-070 - Create save event API
WPT-071 - Validate event fields
WPT-072 - View event details
WPT-073 - Display event information
WPT-074 - Display registered Employees count
WPT-075 - Display registered Employee list
WPT-076 - Edit cancel postpone or delete event
WPT-077 - Create edit event function
WPT-078 - Create cancel event function
WPT-079 - Create postpone event function
WPT-080 - Create delete event function
WPT-081 - Employee Dashboard and Profile
WPT-082 - Employee profile management
WPT-083 - Create Employee profile page
WPT-084 - Create edit Employee profile function
WPT-085 - Create resume upload function
WPT-086 - Create Employee profile API
WPT-087 - Employee home dashboard
WPT-088 - Show my applications summary
WPT-089 - Show event registration summary
WPT-090 - Show notifications summary
WPT-091 - Employee Job Dashboard and Applications
WPT-092 - Browse new job postings
WPT-093 - Create job listings page
WPT-094 - Create job search box
WPT-095 - Create job filters
WPT-096 - Create job description page
WPT-097 - Apply for a job
WPT-098 - Create apply button and flow
WPT-099 - Allow apply using existing profile
WPT-100 - Allow apply by filling application form
WPT-101 - Allow resume upload during application
WPT-102 - Create submit application API
WPT-103 - Track my applications
WPT-104 - Create my applications tab
WPT-105 - Display application status
WPT-106 - Create view application details screen
WPT-107 - Create withdraw application function
WPT-108 - Prevent editing after submission
WPT-109 - Employee Event Dashboard and RSVP
WPT-110 - Browse available events
WPT-111 - Create event listings page
WPT-112 - Create event search box
WPT-113 - Create event detail page
WPT-114 - Register for event
WPT-115 - Create RSVP/register button
WPT-116 - Create event registration API
WPT-117 - Show registered status
WPT-118 - Manage registered events
WPT-119 - Create registered events tab
WPT-120 - Show upcoming events
WPT-121 - Show completed events
WPT-122 - Create cancel RSVP function
WPT-123 - Create add to calendar action
WPT-124 - Notifications for Employee and Employer
WPT-125 - Create notification center
WPT-126 - Create notifications UI
WPT-127 - Create notification API
WPT-128 - Show unread notification count
WPT-129 - Contact WayPoint Support
WPT-130 - Create Contact Us page
WPT-131 - Create contact form UI
WPT-132 - Create submit support ticket API
WPT-133 - Create confirmation message after submission
WPT-134 - Create support ticket ID generation
WPT-135 - Database Tables and Core APIs
WPT-136 - Create user and role data model
WPT-137 - Create users table
WPT-138 - Create employer profile table
WPT-139 - Create Employee profile table
WPT-140 - Create jobs and applications data model
WPT-141 - Create jobs table
WPT-142 - Create applications table
WPT-143 - Create application status field
WPT-144 - Create events and registrations data model
WPT-145 - Create events table
WPT-146 - Create event registrations table
WPT-147 - Create event status field
WPT-148 - Testing and Validation
WPT-149 - Test employer portal flows
WPT-150 - Test employer registration and login
WPT-151 - Test employer job management
WPT-152 - Test employer event management
WPT-153 - Test Employee portal flows
WPT-154 - Test Employee registration and login
WPT-155 - Test job search and application flow
WPT-156 - Test event registration and cancellation
WPT-157 - Test shared features
WPT-158 - Test profile menu actions
WPT-159 - Test contact support form
WPT-160 - Test notifications

## Workload Dashboard
WayPoint Workload Dashboard
Team Member | Open Tickets | Assigned Tickets | Assigned SP | Completed SP | Remaining SP | Completion % | In Progress | Testing
Pragna | 13 | 18 | 71 | 18 | 53 | 25.35% | 5 | 0
Vasavi | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Niharika | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Arun | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Giridhar | 1 | 1 | 5 | 0 | 5 | 0% | 0 | 0
Mahesh | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Jhansi | 5 | 5 | 26 | 0 | 26 | 0% | 0 | 0
Geethanjali | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Mani | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Reports & Charts
WayPoint Reports & Charts
Status | Ticket Count | Type | Ticket Count | Module | Ticket Count
Backlog | 150 | Epic | 13 | Authentication | 16
Ready | 0 | Story | 34 | Candidate Dashboard | 0
In Progress | 5 | Task | 112 | Candidate Event Management | 0
Testing | 0 | Subtask | 1 | Candidate Job Management | 0
Done | 5 |  |  | Candidate Portal | 0
|  |  |  | Candidate Profile | 0
|  |  |  | Contact Support | 6
|  |  |  | Data Model | 12
|  |  |  | Data Model and API | 1
|  |  |  | Employer Application Tracking | 5
|  |  |  | Employer Dashboard | 6
|  |  |  | Employer Event Management | 18
|  |  |  | Employer Job Management | 20
|  |  |  | Employer Portal | 1
|  |  |  | Employer Profile | 4
|  |  |  | Notifications | 5
|  |  |  | Project Foundation | 7
|  |  |  | QA | 12
|  |  |  | Quality Assurance | 1
|  |  |  | Shared UI | 3

## Lookup Values
Ticket Types | Statuses | Story Points | Modules
Epic | Backlog | 0 | Authentication
Story | Ready | 1 | Employee Dashboard
Task | In Progress | 2 | Employee Event Management
Subtask | Testing | 3 | Employee Job Management
Bug | Done | 5 | Employee Portal
| In Review | 8 | Employee Profile
|  | 13 | Contact Support
|  | 21 | Data Model
Data Model and API
Employer Application Management
Employer Dashboard
Employer Event Management
Employer Job Management
Employer Portal
Employer Profile
Notifications
Project Foundation
Quality Assurance
Shared UI

## Instructions
How to Use This Workbook
1. Use the Tickets sheet as the main working backlog. | The entire team can update Assignee, Status, Story Points, and Dates there.
2. Add new tickets below the existing table. | Use the next WPT number and keep the Parent ID to preserve Epic > Story > Task > Subtask relationships.
3. Use dropdowns to keep data consistent. | Type, Module, Assignee, Status, and Story Points have built-in dropdowns.
4. Dashboards update automatically. | Home Dashboard, Workload Dashboard, Kanban Board, and Reports & Charts are formula-driven.
5. Completed work rule. | Story points count as completed only when Status equals Done.
6. Roles can be updated later. | Update the Team Members sheet when roles and skills are finalized.
7. No protection or macros. | This workbook has no sheet protection, passwords, locked cells, hidden sheets, or macros — every cell is editable.